## Plan
New Mexico Bridge Project
ED & Hospital MAT Initiation Blueprint (master)
Key:
No action yet
In process
Complete
Milestone not met
Population | Activity to be completed by Hospital | Critical Outcome (minimum) | Exceptional Outcome | Milestone | activity start date | activity finish date | Team member Hospital | Bridge Implementation Support Team | PM = project Manager
HR - human resources
C-suite | Ensure Hospital leadership are aware of and support project | [6 empty] | Julie
Criteria met? |  | color example | color example
C-Suite | Identify NM Bridge project Champions including project manager | [6 empty] | Eric & MGE
Criteria met? |  | color example | color example
C Suite | Engagement by senior leadership is critical to project success. This support should affirm expected time dedicated by champions (identifed above), assignment of local project manager, local administrative support provided, and ideally project reporting at monthly senior leadership meetings, and identification of champions for following phases (inpatient, L&D, etc.) |  |  | Champions for all phases identified: hospitalists, Pharmacy, Inpatient nursing, OB/Gyn, Peds, L&D nursing, prenatal, OP clinic |  |  |  | Eric & MGE
Milestone met? |  |  |  | color example
All staff | Ensure staff participate in stigma training & fundamentals of Buprenorphine Administration in the hospital | [6 empty] | Snehal, Cindy
Criteria met?
| Rationale: Assists all staff to put new procedures in context |  |  | All scheduled readiness training accomplished
Milestone met?
Finance & HR | Develop Project Budget | [6 empty] | Julie, MGE, Sally
Criteria met?
HR & C Suite | Rationale: Grant funding to assist participants to have time for project |  |  | Project budget approved
Milestone met?
HR | Finalize plan to implement role of peer support and hospital placement | [6 empty] | Sally
Criteria met?
| HR, Finance & Social Work/Nsg have finalized plan for Peer Support position and posted job |  |  | Peer support role established
Milestone met?
Prescribers | Eligible prescribing practitioners apply for waiver. | [6 empty] | Eric
Criteria met?
| Rationale: Prescribers throughout hospital are necessary as patients either in withdrawal or with an SUD and at risk can present in any area. While the bridge team will arrange training as needed -- physicians and APCs are not required to complete an X-waiver course to obtain an X-waiver with 30 pt limit. |  |  | Critical Level of waiver applications reached
Milestone met? |  |  |  | MS not met: risk
Outreach | Identify potential referral clinics & residential sites & assign person to contact | [6 empty] | Sally
Criteria met?
Outreach | Explore joining "Open Beds", an electronic & quality platform for referrals | [6 empty] | Sally
Criteria met?
| Rationale: Agreements with quality community clinics and residential sites essential so rapid intake of ED or hospital based individuals can receive access while still influenced by relief of withdrawal pain. |  |  | Plan for outreach in place
Milestone met?
Criteria met
Information Technology | Discuss with EMR vendor their role in project implementation | [6 empty] | Eric
| Rationale: closed loop communication key to rapid & safe response |  |  | Plan for IT in place
Milestone met?
Population | Activity | Critical | Exceptional | Milestone (MS) | activity start date | activity finish date | Team member Hospital | SOR Project Team
Criteria met?
Prescriber competency & comfort with X-waiver | Indentified staff participate on key indications/ contraindications for Bup, 3-day rule process & Bup loading process & indications | [6 empty] | Brandon
Criteria met?
Prescribers | Indentified staff participate in training on availability of help line through poison center: 800-221-1222 or | [6 empty] | Brandon
Criteria met?
All ED staff | Develop ED workflow & protocol including fast-track, 3-day rule, bupe loading option, & referrals | [6 empty] | Eric
Criteria met?
All ED staff | staff participate in training on Workflow: prescribers, nurses, Social Workers | [6 empty] | Eric
Criteria met?
Prescribers | Prescribers report waivers are complete | [6 empty] | Eric
Criteria met?
Prescribers | Indentify agencies to provide telemedicine buprenprphine as needed | [6 empty] | Eric
Criteria met?
| Rationale: All shifts have knowledgeable staff or access to outside help |  |  | Prescribers ready for go-live
Milestone met?
Nursing | RN staff participate in training on Bup Specfics: SL administration, COWS scoring, preparing take home packs, naloxone dispensing, Stigma Reduction, The language of stigma reduction. Withdrawal Versus Overdose identification, Buprenorphine neurobiology (Brief), The power of Storytelling at the bedside and beyond, Using a COWS, Buprenorphine VS Methadone (pros and cons), | [6 empty] | Cindy
Criteria met?
Nursing | All identified nursing staff, peer support and social workers particpate in naloxone distribution, training on use and form requirements. | [6 empty] | Cindy
Criteria met?
Nursing | Develop protocols for care of patients with SUD | Protocols developed and nursing staff knows where to access | Experienced nurse available for consultation |  | Week 1 | Week 4 | Nurse champion designate | Cindy
Criteria met?
Nursing educated; protocols in place; ready for go-live
Milestone met?
Nursery | Develop policy & training for neonatal withdrawal syndrome (NOWS), non-pharmacologic management of NOWS & monitoring of same | [6 empty] | Leslie
Criteria met?
Nursing | Keep vs. Transfer policy developed & trained for babies with NAS | [6 empty] | Leslie
| Rationale: SUD in pregnant and delivering Moms, and babies with neonatal opioid withdrawal syndrome require specialized care. |  |  | NOWS protocols in place and all nurses educated w protocols for care w NAS and NOWS in place
Milestone met?
Pharmacist | Develop guideline for buprenorphine use in the facility | [6 empty] | Eric
Criteria met?
Pharmacist | Procure free Naloxone & instructions for documentation from BHSD: Melissa.Heinz@state.nm.us 505/709-5608 | [6 empty] | Eric
Criteria met?
Pharmacist | Build ED Bup orders, into ED EMR & confirm | [6 empty] | Eric
Criteria met?
Pharmacist & Finance | Build Bup (and Naloxone) take home pack orders into ED EMR | [6 empty] | Eric
Criteria met?
Prescribers | Develop protocol to prescribe and/or dispense adjunctive medications | [6 empty] | Eric
Criteria met?
Pharmacist | Update formulary & communicate with payers | [6 empty] | Eric
Criteria met?
Pharmacist | Place buprenorphine in Pyxis ED & IP (including SL Bupe 8mg & 2 ml SL mono-product) | [6 empty] | Eric
Criteria met?
Pharmacist & Finance | Rationale: Testing of all new orders and protocols before go-live essential for smooth operation |  |  | Formulary & Pyxis system updated & billing test through all payers has positive results
Milestone met?
Pharmacist - outreach | Contact all local pharmacies to ensure stocking of buprenorphine | [6 empty] | Eric
Criteria met?
| Rationale: Inabiity to get prescriptions filled will accelerate defeat & relapse |  |  | Pharmacies dispersed throughout community will stock
Milestone met?
Social Work | Hire or contract with Peer Support Worker (CPSW) | [6 empty] | Sally
Criteria met?
Social Work | Develop supervisory role & protocol | [6 empty] | Sally
Criteria met?
Social Work | Develop/edit NM Bridge Training for SUN | [6 empty] | Cindy
Criteria met?
Social Work | Alternative to hiring own CPSW: Contact Donald Hume, Peer Support Supervisor for e-CPSW support through Presbyterian: dhume@phs.org - 505-288-0977 | [6 empty] | Sally
Criteria met?
Social Work | Train social worker on hospital protocols for CPSW/Substance Use Navigator | [6 empty] | Sally
Criteria met?
CPSW exhibiting knowledge for all responsibilities
Milestone met?
Finance | Hospital Finance Team identify billing or other payment model for NM buprenorphine and SUD related services | [6 empty] | Sally
Criteria met?
Finance | Develop budget for all new services & materials | [6 empty] | Sally
Criteria met?
Billing | Hospital Finance Team Identifies payors & reimbursement regulation/amount for all services/materials, i.e. ED, IP, referral sources | [6 empty] | Sally
Criteria met?
Billing | Hospital Finance Team updates charge master with new billable services | [6 empty] | Sally
Criteria met?
|  |  |  | Billing system updated & a positive test conducted |  |  |  | Sally
Milestone met?
Outreach | Identified staff contacts potential referral sources - both adolescent & adult - OP & residential: Fill out referral workbook | [6 empty] | Sally
Criteria met?
Referral Sources in place & MOUs agreed upon
Milestone met?
IT | Identified IT staff updates screening results template and orders in EMR | [6 empty] | Eric
Criteria met?
IT | Identified IT staff determines levels of access to EMR | [6 empty] | Eric
Criteria met?
IT | Identified IT staff works with Collective Medical (Emer Dept Info Exchange) to develop agreed upon plan | [6 empty] | MGE
Criteria met?
IT | Identified IT staff ensure EDIE (or similar) is active in ED, IP, Clinic, and partner clinics | [6 empty] | MGE
Criteria met?
PM | Ensure a project champion develop protocols for use of EDIE in workflow | [6 empty] | MGE
Criteria met?
Collective Medical - EDIE & referral system | Test EDIE or similar system communications to all sites | [6 empty] | MGE
Criteria met?
HR & pharmacist | Champions ensure all pertinent Depts are trained on system(s) | [6 empty] | MGE
Criteria met?
EMR & EDIE/Synchrony accessible in all Depts/clinics in plan
Milestone met?
Marketing | Champion identifies staff to distribute engagement certificates for off-site participating pharmacies | [6 empty] | MGE
Criteria met?
Marketing | Champion develops and posts laminated signs in hospital regarding buprenorphine treatment for OUD | [6 empty] | MGE
Criteria met?
Marketing | Champion updates website with Hospital news & contact newspapers & radio stations for marketing message | [6 empty] | MGE
Criteria met?
Marketing initiative executed
Milestone met?
GO-LIVE
Hospital Leadership and Champions | Informs all staff and outreach partners of go-live | [6 empty] | Eric
Criteria met?
| Rationale: Among all the job responsibilities of staff, previous training may have faded away and a reminder that this is taking place TODAY is helpful |  |  | All participants ready & informed
Milestone met?
Criteria met?
| Hospital Champion/s create a CQI team w Rx, Nsg, BH, Prescriber, clinic, other | [6 empty] | MGE
Criteria met?
| Hospital Champion/s develop methodology to track quality | [6 empty] | MGE
Criteria met?
CQI team active w feedback loop in place
Milesstone met?
Outreach | Indentified staff contacts Fire Department for EMT drop-off & develop protocols | [6 empty] | Sally
Criteria met?
Outreach | Indentified staff contacts Police Department for PD drop-off & develop protocols | [6 empty] | Sally
Criteria met?
Outreach | Indentified staff contacts NM Crisis Line to develop referrals in & develop protocols | [6 empty] | Sally
Criteria met?
Outreach | Indentified staff develops protocols w NM Crisis | [6 empty] | Sally
Criteria met?
| Rationale: First responders' knowledge of newly developed services for SUD crises will help divert from arrests and other undesirable outcomes |  |  | All willing Depts' protocols in place, trained & active
Milestone met?
Phase I: Readiness
Phase II: Implementation
OPERATIONAL
Note on B55: Sally: revise tip sheet if needed

## Risks
# | Risk | Remediation Plan | Status | Date | Back-up Plan | Remedy complete yes/no | Back-up in place yes/no