## Sheet1
Activity | Date assigned | Responsible - hosp | Hosp Participants | Bridge contact | Completion date
Investigate project success & hurdles w other hospitals |  | Project Champion |  | Phil Seidenberg
Procure C-suite buy-in |  | Project Champion |  | Phil Seidenberg
Decide which Depts (ED, acute care, Clinic(s), Behavioral Health) & when |  | Project Champion | C-suite | Phil Seidenberg
Identify potential champions for each Dept (ED, acute care, clinic, pharmacy, Nsg, Behavioral Health, Billing, project management) |  | Project Champion | C-suite | Phil Seidenberg
Identify risks & potential work-arounds |  | Project Champion | C-suite | Phil Seidenberg
In-house communication of project |  | CEO |  | Phil Seidenberg
Obtain commitment & potential time from all champions |  | Project Champion | All Dept champions | Phil Seidenberg
Identify potential timing, risks & mitigation strategies |  | Project Champion | All Dept champions | Phil Seidenberg
Identify special populations, e.g. maternity, NICU, Behavioral health, Bridge clinics, reluctant participants |  | Project Champion | All Dept champions | Phil Seidenberg
Review Activities & obtain commitment (accountability) |  | Project Champion | All Dept champions | Eric Ketcham, Cindy Ketcham, Sergio Huerta
Schedule all training (including special populations) |  | Project Champion | All Dept champions | Eric Ketcham, (ED/acute care, & pharmacists) Cindy Ketcham, (NSG, SW) Sergio Huerta, (clinic) Leslie Hayes (OB, NICU) Snehal Bhatt (stigma) Sally Wait (billing & budget)
Develop Project budget |  | Project Champion | Finance | Sally Wait
Identify potential referral sites & obtain comittment for a MOU (pediatric, adolescent, adult, OP, residential)- invite to trainings |  | Project Champion |  | Sally Wait, Eric Ketcham
Secure off-hours telemedicine contract |  | Project Champion |  | Eric Ketcham
Discuss w EMR vendor scope & participation |  | Project Champion |  | Eric Ketcham
All trainings conducted |  | Project Champion | All Dept champions | Eric Ketcham, Cindy Ketcham & others as identified
Develop protocols for care of patients with SUD |  | Project Champion | All Dept champions | Eric Ketcham, Cindy Ketcham & others as identified
Develop guidelines for buprenorphine use |  | Pharmacist | Provider champions | Eric Ketcham
Procure free Naloxone & instructions for use: stock |  | Pharmacy champion | Project Champion | Julie Salvador
Build ED Bup order into ED EMR & confirm |  | Pharmacy champion | Project Champion | Eric Ketcham
Build Bup (and Naloxone) take home pack orders into ED EMR |  | Pharmacy champion | Project Champion | Eric Ketcham
Develop protocol to prescribe and/or dispense adjunctive medications |  | Pharmacy champion | Provider champions | Eric Ketcham
Update formulary & communicate with payers |  | Pharmacy champion | Project Champion | Eric Ketcham
Place buprenorphine in Pyxis - ED, IP , clinic |  | Pharmacy champion | Project Champion | Eric Ketcham
Contact all local pharmacies for stocking of buprenorphine |  | Pharmacy champion | Project Champion | Brandon Warrick
Educate all depts on UNM Poison Center clinician information line |  | Project Champion | All champions | Brandon Warrick
Identify services & determine if billable or overhead |  | Billing champion | finance | Sally Wait
Update charge master w new billable services |  | Billing champion | finance | Sally Wait
Create documentation & coding guidelines for all depts |  | Billing champion | finance | Sally Wait
Create budget items for all new services and materials |  | Billing champion | finance | Sally Wait
Update referral List & enter into EMR if possible |  | Project Champion |  | Sally Wait, Eric Ketcham
All Depts begin activities & document problems |  | Project Champion | All Dept champions | Eric Ketcham, Cindy Ketcham
Inform all out-reach partners of go-live |  | Project Champion
Champion Team Meetings for issue resolution |  | Project Champion | All Dept champions | Eric Ketcham, Cindy Ketcham
Develop Quality Service Review guidelines |  | Project Champion | All Dept champions | Eric Ketcham, Cindy Ketcham
Produce & distribute Rx certificates for off-site participating pharmacies |  | Project Champion | Pharmacy Champion | Eric Ketcham
Produce & distribute laminated signs re. SUD treatment to decided upon locations |  | Project Champion | All Dept champions | Eric Ketcham
Update website with Hospital news & contact newspapers & radio stations for marketing message |  | Project Champion | C-suite
Contact Fire Department for EMT drop-off & develop protocols |  | Project Champion | C-suite | Brandon Warrick
Contact Police Department for PD drop-off & develop protocols |  | Project Champion | C-suite | Brandon Warrick
Contact NM Crisis Line to develop referrals in & develop protocols |  | Project Champion | ED & clinic champions | Brandon Warrick
Peer Support
Phase I - planning
Investigate rationale for adding peer support |  | Project Champion | ED, Clinic, Nsg, SW champions | Donald Hume, Sally Wait
Identify risks & potential work-arounds |  | Project Champion | C-suite | Phil Seidenberg
Decide on placement, e.g. ED or clinic |  | Project Champion | ED, Clinic, Nsg, SW champions | Donald Hume, Sally Wait
Assign Peer Support Champion |  | Project Champion | ED, Clinic, Nsg, SW champions | Donald Hume
Decide on coverage & # of CPSWs - e.g. 24/7 or other |  | Peer Champion | ED, Clinic, Nsg, SW champions | Donald Hume, Sally Wait
If not 24/7 decide on off-site remote coverage |  | Peer Champion | ED, Clinic, Nsg, SW champions | Donald Hume, Brandon Warrick
Decide on supervision |  | Peer Champion | ED, Clinic, Nsg, SW champions | Donald Hume, Sally Wait
Decide on needed training |  | Peer Champion | ED, Clinic, Nsg, SW champions | Donald Hume
Investigate HR policies on hiring & edit, if needed |  | Project Champion | Peer champion, HR | Eric Ketcham
Develop job description & Post |  | Peer Champion | Peer champion, HR, finance | Donald Hume
Hire certified peer support worker(s) |  | Peer Champion | finance, peer champion | Donald Hume
Schedule trainings |  | Peer Champion | Dept of peer & others | Donald Hume
Negotiate contract if remote |  | Project Champion | Finance, peer champion | Donald Hume
Peer Support - Phase II - Implementation
Decide type of activities for peer |  | Peer Champion | Dept of peer & others | Donald Hume, Sally Wait
Develop budget or the Peer program |  | Project Champion | Peer champion | Sally Wait
Develop intra and inter-dept procedures |  | Peer Champion | Dept of peer & others | Donald Hume
Conduct all scheduled trainings |  | Peer Champion | Dept of peer & others | Donald Hume
Develop billing codes & procedures |  | Peer Champion | Billing champion, finance | Sally Wait
Update charge master w new billable services |  | Billing champion | finance, peer champion | Sally Wait
Peer Support - Phase III - Go-live & follow-up
Inform off-site partners of go-live |  | Peer Champion | Project champion | Donald Hume
All affected Depts begin activities & document problems |  | Peer Champion | All Dept champions, remote sites | Donald Hume, Sally Wait
Champion Team Meetings for issue resolution |  | Peer Champion | All Dept champions Project champion, CPSW supervisors, CPSWs, remote sites | Eric Ketcham, Cindy Ketcham, Donald Hume, Sally Wait
Develop Quality Service Review guidelines |  | Treatment | Sally Wait | Eric Ketcham, Cindy Ketcham, Donald Hume, Sally Wait
SBIRT - Screening, Brief Intervention & referral to Treatment
Overview: SBIRT is used in physical healthcare settings to identify, reduce and prevent problematic substance use or misuse and co-occurring mental health disorders such as depression, anxiety, or trauma, as an early intervention. SBIRT is delivered through universal screening, scoring the screening tool and a warm hand-off to a SBIRT trained professional who conducts a face-to-face brief intervention for positive screening results. If the need is identified for additional treatment, the staff member will refer to behavioral health services.
Phase I - planning
Identify a project manager (SBIRT Champion) |  | Project champion | leadership | Phil Seidenberg
Identify provider types to screen, score, and conduct the Brief intervention (BI) |  | SBIRT champion | leadership | Sally Wait
Decide type of activities for each provider type |  | SBIRT champion | leadership | Sally Wait
Identify need for hiring & execute |  | SBIRT champion | Project champion, HR | Sally Wait, Donald Hume
Develop flow chart with staff type for each activity |  | SBIRT champion | leadership | Sally Wait
Develop budget for the SBIRT program, if needed |  | SBIRT champion | leadership | Sally Wait
Schedule all trainings with Life Link Training Institute |  | SBIRT champion |  | Sally Wait
SBIRT Phase II - Implementation
Develop intra and inter-dept procedures |  | SBIRT champion |  | Sally Wait, Donald Hume
Conduct all scheduled trainings |  | SBIRT champion |  | Sally Wait
Develop billing codes & procedures for all payor types |  | SBIRT champion | Billing lead | Sally Wait
Update charge master |  | SBIRT champion | Billing lead | Sally Wait
Conduct MOUs with all referral sites |  | SBIRT champion | leadership | Sally Wait, Eric Ketcham
Develop referral sheet & enter into EMR, (if that is the way referrals are done) |  | SBIRT champion | Information tech | Sally Wait
Enroll all certified staff in Medicaid |  | SBIRT champion |  | Sally Wait
SBIRT- Phase III - Go-live & follow-up
Inform off-site partners of go-live |  | SBIRT Champion | Project champion | Sally Wait
All affected Depts begin activities & document problems |  | SBIRT Champion | All Dept champions, remote sites | Donald Hume, Sally Wait
Champion Team Meetings for issue resolution |  | SBIRT Champion | All Dept champions Project champion, CPSW supervisors, CPSWs, remote sites | Eric Ketcham, Cindy Ketcham, Donald Hume, Sally Wait
Develop Quality Service Review guidelines |  | Quality team | Sally Wait | Eric Ketcham, Cindy Ketcham, Donald Hume, Sally Wait
Phase II: Planning
Phase III: Implementation
Phase IV: Go-Live & Follow-up
Phase V: Optional Add-ons